## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Chess Playing Robotic Arm
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2026-07-01 |  |  |  |  | July | [20 empty] | August | [13 empty] | September | [13 empty] | October
Scrolling increment: | 0 | time axis 2026-07-01 to 2026-10-19
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-07-01 to 2026-10-19
Requirement Analysis & Planning | High Risk |  | 100% | 2026-07-01 | 25
Hardware Selection & Procurement | Med Risk |  | 100% | 2026-07-03 | 10
Hardware Setup | Med Risk |  | 100% | 2026-07-13 | 12
Piece Recognition & Move Detection | Low Risk |  | 100% | 2026-07-20 | 35
Coordinate Mapping & Motion Planning | Med Risk |  | 60% | 2026-07-27 | 30
Mid Semester 1 Examination | Goal |  | - | 2026-08-03 | 6 | 2026-08-04: 2; 2026-08-06: 2; 2026-08-08: 2
Camera Calibration & Board Monitoring | Low Risk |  | 100% | 2026-08-20 | 10
Robotic Arm Control | Med Risk |  | 80% | 2026-08-25 | 27
Chess AI Integration | Low Risk |  | 100% | 2026-08-30 | 5
Game Management & User Interface | Low Risk |  | 75% | 2026-09-05 | 15
Mid Semester 2 Examination | Goal |  | - | 2026-09-21 | 6 | 2026-09-21: 2; 2026-09-23: 2; 2026-09-25: 2
System Integration | On Track |  | 20% | 2026-09-27 | 11
Testing & Optimization | On Track |  | 0% | 2026-10-01 | 15

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2026-09-26 |  |  |  |  | October | [34 empty] | November
Scrolling increment: | 5 | time axis 2026-10-01 to 2026-11-25
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2026-09-26 | 3
Task 2 | Milestone |  |  | 2026-10-01 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2026-09-23 | 10
Task 4 | Milestone |  |  | 2026-10-16 | 1 | bar: F
Task 5 | Med Risk |  | 10% | 2026-10-02 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-10-02 | 13
Task 2 | On Track |  | 50% | 2026-10-04 | 9
Task 3 | Low Risk |  | 33% | 2026-10-09 | 11
Task 4 | Milestone |  |  | 2026-10-11 | 1 | bar: S
Task 5 |  |  |  | 2026-10-12 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-10-11 | 4
Task 2 | Med Risk |  |  | 2026-10-14 | 14
Task 3 | On Track |  |  | 2026-10-29 | 6
Task 4 | Goal |  |  | 2026-11-02 | 3 | M: 2; T: 2; W: 2
Task 5 | Low Risk |  |  | 2026-10-02 | 19
TITLE 4
Task 1 |  |  |  | 2026-11-05 | 15
Task 2 |  |  |  | 2026-11-19 | 5
Task 3 | Milestone |  |  | 2026-12-31 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2026-09-26 |  |  |  |  | October | [34 empty] | November
Scrolling increment: | 5 | time axis 2026-10-01 to 2026-11-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-10-01 to 2026-11-25
TITLE 1
Task 1 | Goal | Name | 25% | 2026-09-26 | 3
Task 2 | Milestone |  |  | 2026-10-01 | 1 | bar: 2026-10-01
Task 3 | Low Risk |  | 50% | 2026-09-23 | 10
Task 4 | Milestone |  |  | 2026-10-16 | 1 | bar: 2026-10-16
Task 5 | Med Risk |  | 10% | 2026-10-02 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-10-02 | 13
Task 2 | On Track |  | 50% | 2026-10-04 | 9
Task 3 | Low Risk |  | 33% | 2026-10-09 | 11
Task 4 | Milestone |  |  | 2026-10-11 | 1 | bar: 2026-10-11
Task 5 |  |  |  | 2026-10-12 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-10-11 | 4
Task 2 | Med Risk |  |  | 2026-10-14 | 14
Task 3 | On Track |  |  | 2026-10-29 | 6
Task 4 | Goal |  |  | 2026-11-02 | 3 | 2026-11-02: 2; 2026-11-03: 2; 2026-11-04: 2
Task 5 | Low Risk |  |  | 2026-10-02 | 19
TITLE 4
Task 1 |  |  |  | 2026-11-05 | 15
Task 2 |  |  |  | 2026-11-19 | 5
Task 3 | Milestone |  |  | 2026-12-31 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one